## Slide 1
PROJECT
PLANNING
The Basics of Capital and Reserve Projects

## Slide 2
PRESENTERS
Josh has been working with communities for over a decade in the PNW. His team has successfully conducted large-scale upgrades and replacement projects for our clients. He holds his General Contractor’s license in OR and WA.
Caren serves as the Branch President for Blue Mountain. She has been in the HOA industry for 25 years and has extensive experience with a wide variety of capital and reserve projects. She holds her PCAM designation as well as her General Contractor’s License.
CAREN FEWELL
JOSH PORTER

## Slide 3
TYPES OF PROJECTS
CAPITAL
RESERVE
EMERGENCY
New additions
Repair or replacement of existing components
Unforeseen events

## Slide 4
CAPITAL PROJECTS
  Improvement Projects
  Cannot be funded through reserves
  Funding may come from:
    Operating funds
    Working Capital
    Special Assessment

## Slide 5
RESERVE PROJECTS
REPAIR
REPLACEMENT
Major repairs (not routine)
Examples: Roofing repairs to more than one unit; landscape refurbishment
Complete replacement
Can include upgrading

## Slide 6
These steps refer to either Capital or Reserve projects
RFP PROCESS (INCLUDING BID WALK AND COMPARING BIDS)
STEPS OF A PROJECT
IDENTIFY THE PROJECT/CREATE SCOPE OF WORK
NEGOTIATE/SELECT VENDOR
SCHEDULE PROJECT
COMMUNICATE

## Slide 7
PLAN
STEP ONE: IDENTIFY THE PROJECT
Is this capital or reserve?
Where is the funding coming from?
If it’s a replacement, are we replacing like or like, or upgrading?
REQUESTS
RESERVE STUDY
ENHANCEMENT
FUNDING

## Slide 8
GENERAL CONTRACTOR
SPECIALIST
STEP TWO: SCOPE OF WORK
CONSULTANT
NOT THE MANAGER

## Slide 9
This is a formal process that spells out the scope of work and any other specific details such as timing, etc. This allows bids to be comparable.
STEP THREE: REQUEST FOR PROPOSAL

## Slide 10
STEP FOUR: BID WALK OR QUESTIONS
WALK WITH ALL BIDDERS
ANSWER QUESTIONS
EVEN PLAYING FIELD
ACCURATE INFO

## Slide 11
STEP FIVE: COMPARE BIDS
CONTRACT PRICE
1
2
3
4
MATERIALS
WARRANTY
TIMING
Be sure that materials are included in the bid, and that the type of materials is what was specified in the RFP.
Look at the warranty and compare between bids. If you are using a General Contractor, ask about double warranty (GC and subs).
Does the timing fit with what the Board is looking for? A lower price may mean waiting longer for the project to start or conclude.
The lowest bidder may not be the best bid. Price should be a consideration, but not the only one.
Negotiate if needed - if one item is off but the rest of the bid is great, talk to them!

## Slide 12
STEP SIX: SELECT VENDOR/SIGN CONTRACT
When should your attorney review a contract?
Who can sign a contract? (hint: this should not be your manager!)

## Slide 13
STEP SEVEN: SCHEDULE THE WORK
A general contractor can be very helpful here!
If your manager is scheduling, it is most likely an extra charge.

## Slide 14
STEP EIGHT: COMMUNICATE
Make sure everyone knows what’s happening!
  Post on portal
  Signs on bulletin boards or mailboxes
  Doorhangers
  Email blast

## Slide 15
WHAT ABOUT EMERGENCIES?
HANDLE IMMEDIATE ISSUE
1
2
3
4
EVALUATE
INSURANCE?
FOLLOW STEPS
Do you have time to get bids, or is the unit/space unsafe or unlivable?
If this is an insurable loss, don’t wait to contact the insurance agent.
Once the emergency portion is handled, follow steps for bids/contracts to finish the repair.
Stop water flowing, mitigate safety issues

## Slide 16
THANK YOU!
Contact us if you have more questions!
josh@bluemountaincommunity.com
caren@bluemountaincommunity.com